## Risk Review Evidence
RISK REVIEW EVIDENCE REGISTER
Company Name | Mayekar Technologies Pvt. Ltd.
Document Type | Evidence / Sample Record
Evidence Purpose | Demonstrate periodic review of information security risks and treatment effectiveness
Traceability | Risk Register → Risk Treatment → Risk Acceptance → Risk Review
Classification | Internal / Portfolio Sample
Evidence ID | Risk ID | Review Date | Risk Owner | Risk Description | Previous Risk Level | Current Risk Level | Risk Status | Control Status | Treatment Status | Risk Trend | Changes Identified | Review Outcome | Next Review Date | Reviewer | Evidence Reference | Review Status | Remarks
RREV-EVD-001 | RSK-001 | 2026-08-04 | Information Security Manager | Malware Infection affecting Dell Latitude 5440 Laptop due to Antivirus Not Updated | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-001 | Completed | Endpoint protection monitoring in progress
RREV-EVD-002 | RSK-002 | 2026-08-04 | IT Manager | Unauthorized Physical Access affecting HP ProDesk 400 G9 Desktop due to Device Left Unattended | Medium | Medium | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-002 | Completed | Risk accepted after physical security verification
RREV-EVD-003 | RSK-003 | 2026-08-04 | IT Infrastructure Manager | Hardware Failure affecting Dell PowerEdge R750 Server due to Lack of Hardware Redundancy | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-003 | Completed | Hardware upgrade planned in next maintenance cycle
RREV-EVD-004 | RSK-004 | 2026-08-04 | IT Manager | Malware Infection affecting Lenovo ThinkCentre Desktop due to Outdated Operating System | Medium | Medium | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-004 | Completed | Endpoint security controls verified
RREV-EVD-005 | RSK-005 | 2026-08-04 | Administration Manager | Printer Failure affecting HP LaserJet Pro Printer due to Lack of Preventive Maintenance | Low | Low | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-005 | Completed | Low business impact risk accepted
RREV-EVD-006 | RSK-006 | 2026-08-04 | Administration Manager | Unauthorized Access affecting Canon ImageRunner Photocopier due to Default Administrator Credentials | Low | Low | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-006 | Completed | Physical controls verified
RREV-EVD-007 | RSK-007 | 2026-08-04 | Network Administrator | Network Attack affecting Cisco Catalyst Switch due to Outdated Firmware | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-007 | Completed | Network security monitoring ongoing
RREV-EVD-008 | RSK-008 | 2026-08-04 | Network Administrator | Firewall Misconfiguration affecting Fortinet FortiGate Firewall due to Improper Firewall Rule Configuration | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-008 | Completed | Firewall rule review scheduled
RREV-EVD-009 | RSK-009 | 2026-08-04 | Network Administrator | Unauthorized Wi-Fi Access affecting TP-Link Wi-Fi Router due to Weak Wi-Fi Password | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-009 | Completed | Wi-Fi security improvement in progress
RREV-EVD-010 | RSK-010 | 2026-08-04 | IT Infrastructure Manager | Power Failure affecting APC Smart UPS due to Battery Not Tested Regularly | Medium | Medium | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-010 | Completed | UPS maintenance completed
RREV-EVD-011 | RSK-011 | 2026-08-04 | IT Manager | Hardware Failure affecting Dell 24-inch LED Monitor due to Physical Damage | Low | Low | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-011 | Completed | Risk accepted – low impact asset
RREV-EVD-012 | RSK-012 | 2026-08-04 | IT Manager | Unauthorized Use affecting Logitech Wireless Keyboard due to Shared Workstation Usage | Low | Low | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-012 | Completed | Risk accepted – administrative control adequate
RREV-EVD-013 | RSK-013 | 2026-08-04 | IT Manager | Unauthorized Use affecting Logitech Wireless Mouse due to No Device Lock Policy | Low | Low | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-013 | Completed | Risk accepted – administrative control adequate
RREV-EVD-014 | RSK-014 | 2026-08-04 | Information Security Manager | Data Theft affecting WD External Hard Disk 2TB due to Unencrypted Storage Device | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-014 | Completed | Encryption verification scheduled
RREV-EVD-015 | RSK-015 | 2026-08-04 | Information Security Manager | Malware Infection affecting Kingston USB Flash Drive 64GB due to Unauthorized USB Usage | Medium | Medium | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-015 | Completed | USB usage monitoring enabled
RREV-EVD-016 | RSK-016 | 2026-08-04 | IT Infrastructure Manager | Hardware Failure affecting Samsung SSD 1TB due to SSD Wear and Tear | Medium | Medium | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-016 | Completed | Storage health monitoring in progress
RREV-EVD-017 | RSK-017 | 2026-08-04 | Backup Administrator | Ransomware Attack affecting Synology NAS Storage due to Backup Configuration Errors | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-017 | Completed | Backup restoration testing planned
RREV-EVD-018 | RSK-018 | 2026-08-04 | HR Manager | Unauthorized Attendance Manipulation affecting Biometric Attendance Device due to Weak Biometric Access Control | Low | Low | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-018 | Completed | Biometric device functioning normally
RREV-EVD-019 | RSK-019 | 2026-08-04 | Administration Manager | Physical Tampering affecting CCTV Camera due to Camera Blind Spots | Medium | Medium | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-019 | Completed | Physical security controls verified
RREV-EVD-020 | RSK-020 | 2026-08-04 | Administration Manager | Equipment Damage affecting Conference Room Projector due to Improper Equipment Handling | Low | Low | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-020 | Completed | Low impact meeting room asset
RREV-EVD-021 | RSK-021 | 2026-08-04 | System Administrator | Operating System Vulnerability affecting Microsoft Windows 11 Pro due to Delayed Security Updates | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-021 | Completed | Patch deployment scheduled
RREV-EVD-022 | RSK-022 | 2026-08-04 | IT Manager | Software Exploitation affecting Microsoft Office 365 due to Unpatched Software | Medium | Medium | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-022 | Completed | Software license compliance verified
RREV-EVD-023 | RSK-023 | 2026-08-04 | Server Administrator | Server Compromise affecting Microsoft Windows Server 2022 due to Missing Security Patches | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-023 | Completed | Server patching planned
RREV-EVD-024 | RSK-024 | 2026-08-04 | Database Administrator | SQL Injection Attack affecting Microsoft SQL Server 2022 due to Weak Database Access Controls | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-024 | Completed | Database hardening activity in progress
RREV-EVD-025 | RSK-025 | 2026-08-04 | Virtualization Administrator | Hypervisor Exploitation affecting VMware ESXi Hypervisor due to Hypervisor Misconfiguration | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-025 | Completed | Hypervisor security review planned
RREV-EVD-026 | RSK-026 | 2026-08-04 | Database Administrator | Database Compromise affecting Oracle Database 19c due to Weak Database Authentication | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-026 | Completed | Database access review scheduled
RREV-EVD-027 | RSK-027 | 2026-08-04 | IT Manager | Software Vulnerability affecting Adobe Acrobat Pro due to Outdated Software Version | Medium | Medium | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-027 | Completed | Software updated regularly
RREV-EVD-028 | RSK-028 | 2026-08-04 | IT Manager | Malicious Website Access affecting Google Chrome Enterprise due to Users Accessing Malicious Websites | Medium | Medium | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-028 | Completed | Web filtering policy implemented
RREV-EVD-029 | RSK-029 | 2026-08-04 | IT Manager | Browser Exploitation affecting Microsoft Edge due to Outdated Browser Version | Medium | Medium | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-029 | Completed | Browser security configuration verified
RREV-EVD-030 | RSK-030 | 2026-08-04 | Endpoint Security Administrator | Malware Infection affecting Microsoft Defender for Endpoint due to Improper Endpoint Protection Configuration | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-030 | Completed | Endpoint monitoring ongoing
RREV-EVD-031 | RSK-031 | 2026-08-04 | HR Manager | Data Leakage affecting Employee HR Records due to Excessive User Privileges | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-031 | Completed | HR data access review scheduled
RREV-EVD-032 | RSK-032 | 2026-08-04 | Database Administrator | Unauthorized Database Access affecting Customer Database due to Weak Access Control Mechanism | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-032 | Completed | Database access monitoring enabled
RREV-EVD-033 | RSK-033 | 2026-08-04 | Procurement Manager | Vendor Information Disclosure affecting Vendor Database due to Third-Party Access Risks | High | High | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-033 | Completed | Supplier security review completed
RREV-EVD-034 | RSK-034 | 2026-08-04 | Finance Manager | Financial Fraud affecting Financial Records due to Improper Financial Data Access Controls | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-034 | Completed | Financial controls under review
RREV-EVD-035 | RSK-035 | 2026-08-04 | HR Manager | Payroll Data Leakage affecting Payroll Records due to Weak Payroll Access Permissions | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-035 | Completed | Payroll access review scheduled
RREV-EVD-036 | RSK-036 | 2026-08-04 | HR Manager | Unauthorized HR Data Access affecting Employee Personal Files due to Unauthorized HR Record Access | Critical | Critical | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-036 | Completed | HR record protection verified
RREV-EVD-037 | RSK-037 | 2026-08-04 | Information Security Manager | Unauthorized Modification affecting ISMS Documentation due to Inadequate Document Version Control | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-037 | Completed | Document review in progress
RREV-EVD-038 | RSK-038 | 2026-08-04 | Information Security Manager | Unauthorized Access affecting Risk Register due to Unauthorized Register Modification | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-038 | Completed | Risk register reviewed quarterly
RREV-EVD-039 | RSK-039 | 2026-08-04 | Information Security Manager | Unauthorized Modification affecting Statement of Applicability (SoA) due to Improper Change Management | High | High | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-039 | Completed | SoA reviewed and approved
RREV-EVD-040 | RSK-040 | 2026-08-04 | Lead Internal Auditor | Audit Evidence Tampering affecting Internal Audit Report due to Insufficient Audit Evidence Protection | High | High | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-040 | Completed | Audit evidence verified
RREV-EVD-041 | RSK-041 | 2026-08-04 | Backup Administrator | Backup Failure affecting Backup Server due to Backup Not Verified Regularly | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-041 | Completed | Backup testing scheduled
RREV-EVD-042 | RSK-042 | 2026-08-04 | File Server Administrator | Unauthorized File Access affecting File Server due to Improper File Permissions | High | High | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-042 | Completed | File permission review planned
RREV-EVD-043 | RSK-043 | 2026-08-04 | Mail Administrator | Email Spoofing affecting Mail Server due to Weak Email Authentication (SPF/DKIM/DMARC Not Configured) | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-043 | Completed | Email security monitoring ongoing
RREV-EVD-044 | RSK-044 | 2026-08-04 | Active Directory Administrator | Privilege Escalation affecting Domain Controller due to Excessive Administrative Privileges | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-044 | Completed | Privilege review scheduled
RREV-EVD-045 | RSK-045 | 2026-08-04 | Network Administrator | DNS Poisoning affecting DNS Server due to Improper DNS Configuration | High | High | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-045 | Completed | DNS configuration verified
RREV-EVD-046 | RSK-046 | 2026-08-04 | Network Administrator | DHCP Spoofing affecting DHCP Server due to Improper DHCP Configuration | High | High | Closed | Controls monitored | Implemented | Stable | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-046 | Completed | DHCP security verified
RREV-EVD-047 | RSK-047 | 2026-08-04 | Network Administrator | Unauthorized Remote Access affecting VPN Gateway due to Weak VPN Authentication | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-047 | Completed | VPN access review scheduled
RREV-EVD-048 | RSK-048 | 2026-08-04 | Web Administrator | Web Application Attack affecting Web Server due to Unpatched Web Server | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-048 | Completed | Web server hardening in progress
RREV-EVD-049 | RSK-049 | 2026-08-04 | Application Administrator | Application Exploitation affecting Application Server due to Application Security Vulnerabilities | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-049 | Completed | Application security testing planned
RREV-EVD-050 | RSK-050 | 2026-08-04 | Cloud Administrator | Cloud Data Breach affecting Cloud Storage (Microsoft OneDrive) due to Misconfigured Cloud Access Permissions | Critical | Critical | In Progress | Controls monitored | In Progress | Monitoring | No material change identified during scheduled review | Continue monitoring and retain existing treatment unless risk conditions change | 2026-09-30 | ISMS Manager / Risk Owner | Risk Register / Risk Acceptance / RTP – RSK-050 | Completed | Cloud security monitoring ongoing

## Evidence Notes
Risk Review Evidence Notes
Purpose | Portfolio/sample evidence demonstrating periodic risk review and traceability.
Traceability | Each record maps to one existing Risk ID and references the treatment and acceptance workflow.
Review Principle | Risks should be reassessed when material changes occur and at the defined review interval.
Important | Use as sanitized portfolio evidence; do not represent it as evidence from a real certified organization.