## Risk Treatment Evidence
RISK TREATMENT EVIDENCE REGISTER
Company Name | Mayekar Technologies Pvt. Ltd.
Document Type | Evidence / Sample Record
Evidence Purpose | Demonstrate implementation and tracking of risk treatment actions
Source Register | Risk Treatment Plan / Information Security Risk Register
Classification | Internal / Portfolio Sample
Evidence ID | Risk ID | Treatment Date | Risk Owner | Risk Description | Risk Level | Treatment Option | Treatment Action | Control / Mitigation | Residual Risk | Target Date | Treatment Status | Evidence Reference | Effectiveness Review | Closure Status | Remarks
RTP-EVD-001 | RSK-001 | 2026-08-02 | Information Security Manager | Malware Infection affecting Dell Latitude 5440 Laptop due to Antivirus Not Updated | High | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-001 | Review treatment effectiveness during scheduled risk review | Open | Endpoint protection monitoring in progress
RTP-EVD-002 | RSK-002 | 2026-08-02 | IT Manager | Unauthorized Physical Access affecting HP ProDesk 400 G9 Desktop due to Device Left Unattended | Medium | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-002 | Review treatment effectiveness during scheduled risk review | Closed | Risk accepted after physical security verification
RTP-EVD-003 | RSK-003 | 2026-08-02 | IT Infrastructure Manager | Hardware Failure affecting Dell PowerEdge R750 Server due to Lack of Hardware Redundancy | High | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-003 | Review treatment effectiveness during scheduled risk review | Open | Hardware upgrade planned in next maintenance cycle
RTP-EVD-004 | RSK-004 | 2026-08-02 | IT Manager | Malware Infection affecting Lenovo ThinkCentre Desktop due to Outdated Operating System | Medium | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-004 | Review treatment effectiveness during scheduled risk review | Closed | Endpoint security controls verified
RTP-EVD-005 | RSK-005 | 2026-08-02 | Administration Manager | Printer Failure affecting HP LaserJet Pro Printer due to Lack of Preventive Maintenance | Low | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-005 | Review treatment effectiveness during scheduled risk review | Closed | Low business impact risk accepted
RTP-EVD-006 | RSK-006 | 2026-08-02 | Administration Manager | Unauthorized Access affecting Canon ImageRunner Photocopier due to Default Administrator Credentials | Low | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-006 | Review treatment effectiveness during scheduled risk review | Closed | Physical controls verified
RTP-EVD-007 | RSK-007 | 2026-08-02 | Network Administrator | Network Attack affecting Cisco Catalyst Switch due to Outdated Firmware | High | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-007 | Review treatment effectiveness during scheduled risk review | Open | Network security monitoring ongoing
RTP-EVD-008 | RSK-008 | 2026-08-02 | Network Administrator | Firewall Misconfiguration affecting Fortinet FortiGate Firewall due to Improper Firewall Rule Configuration | High | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-008 | Review treatment effectiveness during scheduled risk review | Open | Firewall rule review scheduled
RTP-EVD-009 | RSK-009 | 2026-08-02 | Network Administrator | Unauthorized Wi-Fi Access affecting TP-Link Wi-Fi Router due to Weak Wi-Fi Password | High | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-009 | Review treatment effectiveness during scheduled risk review | Open | Wi-Fi security improvement in progress
RTP-EVD-010 | RSK-010 | 2026-08-02 | IT Infrastructure Manager | Power Failure affecting APC Smart UPS due to Battery Not Tested Regularly | Medium | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-010 | Review treatment effectiveness during scheduled risk review | Closed | UPS maintenance completed
RTP-EVD-011 | RSK-011 | 2026-08-02 | IT Manager | Hardware Failure affecting Dell 24-inch LED Monitor due to Physical Damage | Low | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-011 | Review treatment effectiveness during scheduled risk review | Closed | Risk accepted – low impact asset
RTP-EVD-012 | RSK-012 | 2026-08-02 | IT Manager | Unauthorized Use affecting Logitech Wireless Keyboard due to Shared Workstation Usage | Low | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-012 | Review treatment effectiveness during scheduled risk review | Closed | Risk accepted – administrative control adequate
RTP-EVD-013 | RSK-013 | 2026-08-02 | IT Manager | Unauthorized Use affecting Logitech Wireless Mouse due to No Device Lock Policy | Low | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-013 | Review treatment effectiveness during scheduled risk review | Closed | Risk accepted – administrative control adequate
RTP-EVD-014 | RSK-014 | 2026-08-02 | Information Security Manager | Data Theft affecting WD External Hard Disk 2TB due to Unencrypted Storage Device | High | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-014 | Review treatment effectiveness during scheduled risk review | Open | Encryption verification scheduled
RTP-EVD-015 | RSK-015 | 2026-08-02 | Information Security Manager | Malware Infection affecting Kingston USB Flash Drive 64GB due to Unauthorized USB Usage | Medium | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-015 | Review treatment effectiveness during scheduled risk review | Closed | USB usage monitoring enabled
RTP-EVD-016 | RSK-016 | 2026-08-02 | IT Infrastructure Manager | Hardware Failure affecting Samsung SSD 1TB due to SSD Wear and Tear | Medium | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-016 | Review treatment effectiveness during scheduled risk review | Open | Storage health monitoring in progress
RTP-EVD-017 | RSK-017 | 2026-08-02 | Backup Administrator | Ransomware Attack affecting Synology NAS Storage due to Backup Configuration Errors | High | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-017 | Review treatment effectiveness during scheduled risk review | Open | Backup restoration testing planned
RTP-EVD-018 | RSK-018 | 2026-08-02 | HR Manager | Unauthorized Attendance Manipulation affecting Biometric Attendance Device due to Weak Biometric Access Control | Low | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-018 | Review treatment effectiveness during scheduled risk review | Closed | Biometric device functioning normally
RTP-EVD-019 | RSK-019 | 2026-08-02 | Administration Manager | Physical Tampering affecting CCTV Camera due to Camera Blind Spots | Medium | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-019 | Review treatment effectiveness during scheduled risk review | Closed | Physical security controls verified
RTP-EVD-020 | RSK-020 | 2026-08-02 | Administration Manager | Equipment Damage affecting Conference Room Projector due to Improper Equipment Handling | Low | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-020 | Review treatment effectiveness during scheduled risk review | Closed | Low impact meeting room asset
RTP-EVD-021 | RSK-021 | 2026-08-02 | System Administrator | Operating System Vulnerability affecting Microsoft Windows 11 Pro due to Delayed Security Updates | High | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-021 | Review treatment effectiveness during scheduled risk review | Open | Patch deployment scheduled
RTP-EVD-022 | RSK-022 | 2026-08-02 | IT Manager | Software Exploitation affecting Microsoft Office 365 due to Unpatched Software | Medium | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-022 | Review treatment effectiveness during scheduled risk review | Closed | Software license compliance verified
RTP-EVD-023 | RSK-023 | 2026-08-02 | Server Administrator | Server Compromise affecting Microsoft Windows Server 2022 due to Missing Security Patches | High | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-023 | Review treatment effectiveness during scheduled risk review | Open | Server patching planned
RTP-EVD-024 | RSK-024 | 2026-08-02 | Database Administrator | SQL Injection Attack affecting Microsoft SQL Server 2022 due to Weak Database Access Controls | Critical | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-024 | Review treatment effectiveness during scheduled risk review | Open | Database hardening activity in progress
RTP-EVD-025 | RSK-025 | 2026-08-02 | Virtualization Administrator | Hypervisor Exploitation affecting VMware ESXi Hypervisor due to Hypervisor Misconfiguration | High | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-025 | Review treatment effectiveness during scheduled risk review | Open | Hypervisor security review planned
RTP-EVD-026 | RSK-026 | 2026-08-02 | Database Administrator | Database Compromise affecting Oracle Database 19c due to Weak Database Authentication | Critical | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-026 | Review treatment effectiveness during scheduled risk review | Open | Database access review scheduled
RTP-EVD-027 | RSK-027 | 2026-08-02 | IT Manager | Software Vulnerability affecting Adobe Acrobat Pro due to Outdated Software Version | Medium | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-027 | Review treatment effectiveness during scheduled risk review | Closed | Software updated regularly
RTP-EVD-028 | RSK-028 | 2026-08-02 | IT Manager | Malicious Website Access affecting Google Chrome Enterprise due to Users Accessing Malicious Websites | Medium | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-028 | Review treatment effectiveness during scheduled risk review | Closed | Web filtering policy implemented
RTP-EVD-029 | RSK-029 | 2026-08-02 | IT Manager | Browser Exploitation affecting Microsoft Edge due to Outdated Browser Version | Medium | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-029 | Review treatment effectiveness during scheduled risk review | Closed | Browser security configuration verified
RTP-EVD-030 | RSK-030 | 2026-08-02 | Endpoint Security Administrator | Malware Infection affecting Microsoft Defender for Endpoint due to Improper Endpoint Protection Configuration | High | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-030 | Review treatment effectiveness during scheduled risk review | Open | Endpoint monitoring ongoing
RTP-EVD-031 | RSK-031 | 2026-08-02 | HR Manager | Data Leakage affecting Employee HR Records due to Excessive User Privileges | Critical | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-031 | Review treatment effectiveness during scheduled risk review | Open | HR data access review scheduled
RTP-EVD-032 | RSK-032 | 2026-08-02 | Database Administrator | Unauthorized Database Access affecting Customer Database due to Weak Access Control Mechanism | Critical | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-032 | Review treatment effectiveness during scheduled risk review | Open | Database access monitoring enabled
RTP-EVD-033 | RSK-033 | 2026-08-02 | Procurement Manager | Vendor Information Disclosure affecting Vendor Database due to Third-Party Access Risks | High | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-033 | Review treatment effectiveness during scheduled risk review | Closed | Supplier security review completed
RTP-EVD-034 | RSK-034 | 2026-08-02 | Finance Manager | Financial Fraud affecting Financial Records due to Improper Financial Data Access Controls | Critical | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-034 | Review treatment effectiveness during scheduled risk review | Open | Financial controls under review
RTP-EVD-035 | RSK-035 | 2026-08-02 | HR Manager | Payroll Data Leakage affecting Payroll Records due to Weak Payroll Access Permissions | Critical | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-035 | Review treatment effectiveness during scheduled risk review | Open | Payroll access review scheduled
RTP-EVD-036 | RSK-036 | 2026-08-02 | HR Manager | Unauthorized HR Data Access affecting Employee Personal Files due to Unauthorized HR Record Access | Critical | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-036 | Review treatment effectiveness during scheduled risk review | Closed | HR record protection verified
RTP-EVD-037 | RSK-037 | 2026-08-02 | Information Security Manager | Unauthorized Modification affecting ISMS Documentation due to Inadequate Document Version Control | High | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-037 | Review treatment effectiveness during scheduled risk review | Open | Document review in progress
RTP-EVD-038 | RSK-038 | 2026-08-02 | Information Security Manager | Unauthorized Access affecting Risk Register due to Unauthorized Register Modification | High | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-038 | Review treatment effectiveness during scheduled risk review | Open | Risk register reviewed quarterly
RTP-EVD-039 | RSK-039 | 2026-08-02 | Information Security Manager | Unauthorized Modification affecting Statement of Applicability (SoA) due to Improper Change Management | High | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-039 | Review treatment effectiveness during scheduled risk review | Closed | SoA reviewed and approved
RTP-EVD-040 | RSK-040 | 2026-08-02 | Lead Internal Auditor | Audit Evidence Tampering affecting Internal Audit Report due to Insufficient Audit Evidence Protection | High | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-040 | Review treatment effectiveness during scheduled risk review | Closed | Audit evidence verified
RTP-EVD-041 | RSK-041 | 2026-08-02 | Backup Administrator | Backup Failure affecting Backup Server due to Backup Not Verified Regularly | High | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-041 | Review treatment effectiveness during scheduled risk review | Open | Backup testing scheduled
RTP-EVD-042 | RSK-042 | 2026-08-02 | File Server Administrator | Unauthorized File Access affecting File Server due to Improper File Permissions | High | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-042 | Review treatment effectiveness during scheduled risk review | Open | File permission review planned
RTP-EVD-043 | RSK-043 | 2026-08-02 | Mail Administrator | Email Spoofing affecting Mail Server due to Weak Email Authentication (SPF/DKIM/DMARC Not Configured) | Critical | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-043 | Review treatment effectiveness during scheduled risk review | Open | Email security monitoring ongoing
RTP-EVD-044 | RSK-044 | 2026-08-02 | Active Directory Administrator | Privilege Escalation affecting Domain Controller due to Excessive Administrative Privileges | Critical | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-044 | Review treatment effectiveness during scheduled risk review | Open | Privilege review scheduled
RTP-EVD-045 | RSK-045 | 2026-08-02 | Network Administrator | DNS Poisoning affecting DNS Server due to Improper DNS Configuration | High | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-045 | Review treatment effectiveness during scheduled risk review | Closed | DNS configuration verified
RTP-EVD-046 | RSK-046 | 2026-08-02 | Network Administrator | DHCP Spoofing affecting DHCP Server due to Improper DHCP Configuration | High | Mitigate | Implement preventive controls and strengthen monitoring | Access control, monitoring and periodic review | Residual risk monitored after treatment | 2026-09-30 | Implemented | MTPL-RTP-EVD-046 | Review treatment effectiveness during scheduled risk review | Closed | DHCP security verified
RTP-EVD-047 | RSK-047 | 2026-08-02 | Network Administrator | Unauthorized Remote Access affecting VPN Gateway due to Weak VPN Authentication | Critical | Mitigate | Restrict access and enforce periodic review | Least privilege and access review | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-047 | Review treatment effectiveness during scheduled risk review | Open | VPN access review scheduled
RTP-EVD-048 | RSK-048 | 2026-08-02 | Web Administrator | Web Application Attack affecting Web Server due to Unpatched Web Server | Critical | Mitigate | Apply security configuration hardening | Secure configuration baseline | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-048 | Review treatment effectiveness during scheduled risk review | Open | Web server hardening in progress
RTP-EVD-049 | RSK-049 | 2026-08-02 | Application Administrator | Application Exploitation affecting Application Server due to Application Security Vulnerabilities | Critical | Mitigate | Increase monitoring and alerting coverage | Security monitoring and incident response | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-049 | Review treatment effectiveness during scheduled risk review | Open | Application security testing planned
RTP-EVD-050 | RSK-050 | 2026-08-02 | Cloud Administrator | Cloud Data Breach affecting Cloud Storage (Microsoft OneDrive) due to Misconfigured Cloud Access Permissions | Critical | Mitigate | Implement documented security procedure and user awareness | Policy, training and management oversight | Residual risk monitored after treatment | 2026-09-30 | In Progress | MTPL-RTP-EVD-050 | Review treatment effectiveness during scheduled risk review | Open | Cloud security monitoring ongoing

## Evidence Notes
Risk Treatment Evidence Notes
Purpose | Portfolio/sample evidence showing how identified risks are treated and monitored.
Traceability | Each record maps to one existing Risk ID from the project Risk Register.
Treatment Principle | Risk treatment actions are aligned to the risk context and existing control environment.
Important | Use as sanitized portfolio evidence; do not represent it as evidence from a real certified organization.