## Sheet1
CONTINUAL IMPROVEMENT REGISTER
Company Name : Mayekar Technologies Pvt. Ltd.
Document Number : MTPL-ISMS-026
Version : 1.0
Classification : Internal
Prepared By : Omkar Abhay Mayekar
Sr. No. | CI ID | Improvement Source | Date Identified | Department | Process / Area | Improvement Opportunity | Current State | Proposed Improvement | Expected Benefit | Risk / Impact | Priority | Improvement Owner | Action Required | Target Date | Status | Implementation Date | Effectiveness Review | Evidence Reference | Approved By | Closure Status | Closure Date | Management Approval | Remarks
1 | CI-001 | Internal Audit | 2026-08-01 | Information Security | ISMS Governance | Improve centralized ISMS document tracking | ISMS documents are tracked through manual records | Implement centralized ISMS document management and tracking | Improved document visibility and version control | Low | High | Information Security Manager | Implement centralized ISMS document management | 2026-08-15 | Completed | 2026-08-14 | Effective | CI-EVD-001 | Aakanksha Abhay Mayekar | Closed | 2026-08-16 | Approved | Document tracking improvement implemented successfully
2 | CI-002 | Risk Assessment | 2026-08-03 | Risk Management | Risk Management | Automate risk assessment review reminders | Risk reviews are scheduled manually | Automate risk assessment review reminders | Timely completion of risk reviews | Medium | Medium | Risk Manager | Configure automated risk review reminders | 2026-08-22 | Completed | 2026-08-21 | Effective | CI-EVD-002 | Aakanksha Abhay Mayekar | Closed | 2026-08-23 | Approved | Risk review automation implemented
3 | CI-003 | Management Review | 2026-08-05 | Management | Management Review | Improve management review action tracking | Management actions are tracked in spreadsheets | Implement centralized management review action tracker | Better accountability for management actions | Low | High | Information Security Manager | Implement centralized management action tracker | 2026-08-29 | In Progress | - | Pending | CI-EVD-003 | Aakanksha Abhay Mayekar | Open | - | Pending | Management review tracking improvement remains open
4 | CI-004 | Security Incident | 2026-08-07 | Security Operations | Incident Management | Enhance incident escalation and closure process | Incident escalation depends on manual communication | Implement automated incident escalation and closure workflow | Faster incident escalation and closure | Medium | High | Incident Manager | Deploy automated incident escalation workflow | 2026-09-05 | Completed | 2026-09-04 | Effective | CI-EVD-004 | Aakanksha Abhay Mayekar | Closed | 2026-09-06 | Approved | Incident workflow improvement implemented
5 | CI-005 | Employee Feedback | 2026-08-09 | Human Resources | Security Awareness | Improve security awareness completion tracking | Training completion is tracked manually | Implement centralized security awareness tracking | Improved training compliance visibility | Low | Medium | HR Manager | Implement centralized awareness tracking | 2026-09-12 | Completed | 2026-09-11 | Effective | CI-EVD-005 | Aakanksha Abhay Mayekar | Closed | 2026-09-13 | Approved | Security awareness tracking improved
6 | CI-006 | KPI Review | 2026-08-11 | Information Security | ISMS Performance Monitoring | Automate ISMS KPI reporting | KPI reports require manual data collection | Automate ISMS KPI data collection and reporting | Accurate and timely KPI reporting | Low | Medium | ISMS Manager | Automate KPI data collection | 2026-09-19 | Completed | 2026-09-18 | Effective | CI-EVD-006 | Aakanksha Abhay Mayekar | Closed | 2026-09-20 | Approved | KPI reporting automation implemented
7 | CI-007 | Internal Audit | 2026-08-13 | IT Infrastructure | IT Infrastructure | Improve infrastructure security monitoring | Infrastructure monitoring has limited centralized visibility | Implement centralized infrastructure security monitoring | Improved infrastructure threat visibility | Medium | High | IT Infrastructure Manager | Deploy centralized infrastructure security monitoring | 2026-09-26 | In Progress | - | Pending | CI-EVD-007 | Aakanksha Abhay Mayekar | Open | - | Pending | Infrastructure monitoring improvement remains open
8 | CI-008 | Risk Assessment | 2026-08-15 | Risk Management | Risk Treatment | Strengthen risk treatment escalation process | Risk treatment follow-up is manually monitored | Implement automated risk treatment escalation | Reduced overdue risk treatments | Medium | High | Risk Manager | Configure risk treatment escalation alerts | 2026-10-03 | Completed | 2026-10-02 | Effective | CI-EVD-008 | Aakanksha Abhay Mayekar | Closed | 2026-10-04 | Approved | Risk treatment escalation implemented
9 | CI-009 | Management Review | 2026-08-17 | Management | Management Review | Improve management review evidence retention | Management review evidence is stored across multiple locations | Centralize management review evidence repository | Improved management review evidence traceability | Low | Medium | Document Controller | Centralize management review evidence | 2026-10-10 | Completed | 2026-10-09 | Effective | CI-EVD-009 | Aakanksha Abhay Mayekar | Closed | 2026-10-11 | Approved | Management review evidence centralized
10 | CI-010 | Security Incident | 2026-08-19 | Security Operations | Incident Response | Enhance incident response documentation | Incident documentation is maintained manually | Standardize incident response documentation and workflow | Consistent incident documentation | Medium | High | Incident Manager | Standardize incident response documentation | 2026-10-17 | In Progress | - | Pending | CI-EVD-010 | Aakanksha Abhay Mayekar | Open | - | Pending | Incident documentation improvement remains open
11 | CI-011 | Supplier Review | 2026-08-21 | Vendor Management | Supplier Management | Automate supplier assessment tracking | Supplier assessments are tracked through spreadsheets | Implement automated supplier assessment tracking | Improved supplier assessment timeliness | Low | Medium | Vendor Manager | Implement supplier assessment tracking | 2026-10-24 | Completed | 2026-10-23 | Effective | CI-EVD-011 | Aakanksha Abhay Mayekar | Closed | 2026-10-25 | Approved | Supplier assessment tracking implemented
12 | CI-012 | Compliance Review | 2026-08-23 | Compliance | Compliance Management | Improve compliance evidence management | Compliance evidence is maintained in separate folders | Centralize compliance evidence management | Faster compliance evidence retrieval | Medium | High | Compliance Manager | Centralize compliance evidence repository | 2026-10-31 | Completed | 2026-10-30 | Effective | CI-EVD-012 | Aakanksha Abhay Mayekar | Closed | 2026-11-01 | Approved | Compliance evidence centralized
13 | CI-013 | Internal Audit | 2026-08-25 | Internal Audit | Internal Audit | Improve internal audit finding tracking | Audit findings are manually tracked | Implement centralized internal audit finding tracker | Improved audit finding closure tracking | Low | High | Lead Internal Auditor | Implement audit finding tracker | 2026-11-07 | In Progress | - | Pending | CI-EVD-013 | Aakanksha Abhay Mayekar | Open | - | Pending | Internal audit tracking improvement remains open
14 | CI-014 | KPI Review | 2026-08-27 | Information Security | KPI Management | Automate KPI dashboard reporting | KPI reporting requires manual consolidation | Develop automated KPI dashboard | Faster management decision-making | Low | Medium | ISMS Manager | Develop automated KPI dashboard | 2026-11-14 | Completed | 2026-11-13 | Effective | CI-EVD-014 | Aakanksha Abhay Mayekar | Closed | 2026-11-15 | Approved | KPI dashboard implemented
15 | CI-015 | Risk Assessment | 2026-08-29 | Risk Management | Risk Assessment | Standardize risk assessment templates | Risk assessment templates are not fully standardized | Standardize organization-wide risk assessment templates | Consistent risk assessment results | Medium | High | Risk Manager | Standardize risk assessment templates | 2026-11-21 | Completed | 2026-11-20 | Effective | CI-EVD-015 | Aakanksha Abhay Mayekar | Closed | 2026-11-22 | Approved | Risk assessment templates standardized
16 | CI-016 | Management Review | 2026-08-31 | Management | ISMS Governance | Improve ISMS document version control | Document version control is manually maintained | Implement controlled document version management | Reduced document control errors | Low | Medium | Document Controller | Implement document version control | 2026-11-28 | Completed | 2026-11-27 | Effective | CI-EVD-016 | Aakanksha Abhay Mayekar | Closed | 2026-11-29 | Approved | Document version control improved
17 | CI-017 | Employee Feedback | 2026-09-02 | Human Resources | Security Awareness | Introduce targeted security awareness campaigns | Awareness campaigns are mainly generic | Introduce role-based security awareness campaigns | Improved employee security awareness | Low | Medium | Security Awareness Manager | Launch role-based security awareness campaigns | 2026-12-05 | In Progress | - | Pending | CI-EVD-017 | Aakanksha Abhay Mayekar | Open | - | Pending | Role-based awareness campaign improvement remains open
18 | CI-018 | Security Incident | 2026-09-04 | Security Operations | Incident Management | Improve incident trend analysis | Incident trends require manual analysis | Implement automated incident trend reporting | Better identification of recurring incidents | Medium | High | SOC Manager | Implement automated incident trend reporting | 2026-12-12 | Completed | 2026-12-11 | Effective | CI-EVD-018 | Aakanksha Abhay Mayekar | Closed | 2026-12-13 | Approved | Incident trend reporting implemented
19 | CI-019 | Internal Audit | 2026-09-06 | Information Security | Information Security | Enhance information security monitoring | Security monitoring reports are generated manually | Centralize information security monitoring dashboards | Improved security visibility | Medium | High | Information Security Manager | Deploy information security monitoring dashboard | 2026-12-19 | Completed | 2026-12-18 | Effective | CI-EVD-019 | Aakanksha Abhay Mayekar | Closed | 2026-12-20 | Approved | Security monitoring dashboard implemented
20 | CI-020 | Supplier Review | 2026-09-08 | Vendor Management | Supplier Security | Improve supplier security performance tracking | Supplier security performance is reviewed periodically | Implement supplier security performance dashboard | Better supplier security oversight | Medium | Medium | Vendor Manager | Implement supplier security performance dashboard | 2026-12-26 | In Progress | - | Pending | CI-EVD-020 | Aakanksha Abhay Mayekar | Open | - | Pending | Supplier performance tracking improvement remains open
21 | CI-021 | KPI Review | 2026-09-10 | IT Infrastructure | Network Security | Strengthen network security monitoring | Network monitoring reports require manual review | Enhance centralized network security monitoring | Faster detection of network threats | High | High | Network Security Manager | Enhance network security monitoring | 2027-01-02 | Completed | 2027-01-01 | Effective | CI-EVD-021 | Aakanksha Abhay Mayekar | Closed | 2027-01-03 | Approved | Network monitoring enhancement implemented
22 | CI-022 | Risk Assessment | 2026-09-12 | Risk Management | Risk Management | Improve risk reporting to management | Risk reports are prepared manually | Automate management risk reporting | Improved management risk visibility | Low | Medium | Risk Manager | Automate management risk reporting | 2027-01-09 | Completed | 2027-01-08 | Effective | CI-EVD-022 | Aakanksha Abhay Mayekar | Closed | 2027-01-10 | Approved | Management risk reporting improved
23 | CI-023 | Management Review | 2026-09-14 | Management | Management Review | Improve management review meeting preparation | Management review preparation is largely manual | Implement standardized management review preparation checklist | More efficient management review preparation | Low | Medium | Information Security Manager | Implement management review preparation checklist | 2027-01-16 | In Progress | - | Pending | CI-EVD-023 | Aakanksha Abhay Mayekar | Open | - | Pending | Management review preparation improvement remains open
24 | CI-024 | Compliance Review | 2026-09-16 | Compliance | Compliance Monitoring | Automate compliance monitoring | Compliance monitoring is spreadsheet-based | Implement automated compliance monitoring dashboard | Improved compliance monitoring | Medium | High | Compliance Manager | Deploy compliance monitoring dashboard | 2027-01-23 | Completed | 2027-01-22 | Effective | CI-EVD-024 | Aakanksha Abhay Mayekar | Closed | 2027-01-24 | Approved | Compliance monitoring dashboard implemented
25 | CI-025 | Internal Audit | 2026-09-18 | Internal Audit | Internal Audit | Improve internal audit evidence collection | Audit evidence collection is manually coordinated | Centralize internal audit evidence repository | Faster audit evidence collection | Low | Medium | Lead Internal Auditor | Centralize audit evidence repository | 2027-01-30 | Completed | 2027-01-29 | Effective | CI-EVD-025 | Aakanksha Abhay Mayekar | Closed | 2027-01-31 | Approved | Audit evidence repository implemented
26 | CI-026 | Security Incident | 2026-09-20 | Security Operations | SOC Operations | Enhance SOC alert correlation | SOC alerts require manual correlation | Enhance SOC alert correlation and prioritization | Reduced SOC alert investigation time | High | Critical | SOC Manager | Enhance SOC alert correlation | 2027-02-06 | In Progress | - | Pending | CI-EVD-026 | Aakanksha Abhay Mayekar | Open | - | Pending | SOC alert correlation improvement remains open
27 | CI-027 | Employee Feedback | 2026-09-22 | Human Resources | Security Awareness | Improve role-based security awareness | Security training is not fully role-specific | Implement role-based security training | Improved role-specific security knowledge | Low | Medium | HR Manager | Develop role-specific security training | 2027-02-13 | Completed | 2027-02-12 | Effective | CI-EVD-027 | Aakanksha Abhay Mayekar | Closed | 2027-02-14 | Approved | Role-based training implemented
28 | CI-028 | KPI Review | 2026-09-24 | Information Security | ISMS Performance | Improve ISMS performance dashboards | ISMS performance dashboards are limited | Develop ISMS performance dashboard | Better visibility of ISMS performance | Low | Medium | ISMS Manager | Implement ISMS performance dashboard | 2027-02-20 | Completed | 2027-02-19 | Effective | CI-EVD-028 | Aakanksha Abhay Mayekar | Closed | 2027-02-21 | Approved | ISMS performance dashboard implemented
29 | CI-029 | Risk Assessment | 2026-09-26 | Risk Management | Risk Treatment | Automate risk treatment status reporting | Risk treatment reporting is manually prepared | Automate risk treatment status reporting | Reduced overdue risk treatments | Medium | High | Risk Manager | Automate risk treatment reporting | 2027-02-27 | In Progress | - | Pending | CI-EVD-029 | Aakanksha Abhay Mayekar | Open | - | Pending | Risk treatment reporting improvement remains open
30 | CI-030 | Management Review | 2026-09-28 | Management | Management Review | Improve management action follow-up | Management action follow-up is spreadsheet-based | Implement management action tracking workflow | Improved management accountability | Low | Medium | Information Security Manager | Implement management action workflow | 2027-03-06 | Completed | 2027-03-05 | Effective | CI-EVD-030 | Aakanksha Abhay Mayekar | Closed | 2027-03-07 | Approved | Management action workflow implemented
31 | CI-031 | Internal Audit | 2026-09-30 | IT Infrastructure | IT Infrastructure | Strengthen infrastructure configuration monitoring | Configuration monitoring is partially automated | Expand automated configuration monitoring | Faster identification of configuration deviations | Medium | High | Configuration Manager | Expand configuration monitoring | 2027-03-13 | Completed | 2027-03-12 | Effective | CI-EVD-031 | Aakanksha Abhay Mayekar | Closed | 2027-03-14 | Approved | Configuration monitoring improved
32 | CI-032 | Supplier Review | 2026-10-02 | Vendor Management | Supplier Management | Improve supplier onboarding security checks | Supplier onboarding security checks are manual | Implement supplier onboarding security checklist | Improved supplier onboarding security | Medium | High | Vendor Manager | Implement supplier onboarding security checklist | 2027-03-20 | In Progress | - | Pending | CI-EVD-032 | Aakanksha Abhay Mayekar | Open | - | Pending | Supplier onboarding security improvement remains open
33 | CI-033 | Security Incident | 2026-10-04 | Security Operations | Incident Response | Enhance incident response workflow automation | Incident workflow is not fully automated | Automate incident response workflow | Faster incident response | High | Critical | Incident Manager | Automate incident response workflow | 2027-03-27 | Completed | 2027-03-26 | Effective | CI-EVD-033 | Aakanksha Abhay Mayekar | Closed | 2027-03-28 | Approved | Incident workflow automation implemented
34 | CI-034 | Compliance Review | 2026-10-06 | Compliance | Compliance Management | Improve compliance obligation tracking | Compliance obligations are manually tracked | Implement centralized compliance obligation register | Improved compliance tracking | Medium | High | Compliance Manager | Implement centralized compliance register | 2027-04-03 | Completed | 2027-04-02 | Effective | CI-EVD-034 | Aakanksha Abhay Mayekar | Closed | 2027-04-04 | Approved | Compliance register centralized
35 | CI-035 | KPI Review | 2026-10-08 | Information Security | Information Security | Improve information security reporting | Information security reporting is fragmented | Develop centralized information security reporting dashboard | Better management reporting | Low | Medium | Information Security Manager | Develop information security reporting dashboard | 2027-04-10 | In Progress | - | Pending | CI-EVD-035 | Aakanksha Abhay Mayekar | Open | - | Pending | Information security reporting improvement remains open
36 | CI-036 | Risk Assessment | 2026-10-10 | Risk Management | Risk Management | Enhance risk assessment consistency | Risk assessment practices vary between processes | Standardize risk assessment methodology and templates | Consistent risk evaluation | Medium | High | Risk Manager | Standardize risk assessment methodology | 2027-04-17 | Completed | 2027-04-16 | Effective | CI-EVD-036 | Aakanksha Abhay Mayekar | Closed | 2027-04-18 | Approved | Risk assessment methodology standardized
37 | CI-037 | Management Review | 2026-10-12 | Management | Management Review | Improve management review decision tracking | Management review decisions are manually recorded | Implement digital management review decision tracker | Improved traceability of decisions | Low | Medium | Information Security Manager | Implement digital management review tracker | 2027-04-24 | Completed | 2027-04-23 | Effective | CI-EVD-037 | Aakanksha Abhay Mayekar | Closed | 2027-04-25 | Approved | Management review decision tracking implemented
38 | CI-038 | Employee Feedback | 2026-10-14 | Human Resources | Security Awareness | Introduce role-specific security training | Security training is mostly standardized | Develop role-specific security training modules | Improved employee security capability | Low | Medium | HR Manager | Develop role-specific security training modules | 2027-05-01 | In Progress | - | Pending | CI-EVD-038 | Aakanksha Abhay Mayekar | Open | - | Pending | Role-specific training improvement remains open
39 | CI-039 | Internal Audit | 2026-10-16 | Internal Audit | Internal Audit | Improve internal audit reporting | Audit reporting requires manual consolidation | Automate internal audit reporting | Faster audit reporting | Low | Medium | Lead Internal Auditor | Automate internal audit reporting | 2027-05-08 | Completed | 2027-05-07 | Effective | CI-EVD-039 | Aakanksha Abhay Mayekar | Closed | 2027-05-09 | Approved | Internal audit reporting automated
40 | CI-040 | Security Incident | 2026-10-18 | Security Operations | SOC Operations | Enhance SOC monitoring capabilities | SOC monitoring requires manual analysis | Enhance SOC monitoring and analytics | Improved SOC detection capability | Medium | High | SOC Manager | Enhance SOC monitoring analytics | 2027-05-15 | Completed | 2027-05-14 | Effective | CI-EVD-040 | Aakanksha Abhay Mayekar | Closed | 2027-05-16 | Approved | SOC analytics improved
41 | CI-041 | Supplier Review | 2026-10-20 | Vendor Management | Supplier Security | Improve supplier risk classification | Supplier risks are classified manually | Implement supplier risk classification framework | Better supplier risk prioritization | Medium | High | Vendor Manager | Implement supplier risk classification | 2027-05-22 | In Progress | - | Pending | CI-EVD-041 | Aakanksha Abhay Mayekar | Open | - | Pending | Supplier risk classification improvement remains open
42 | CI-042 | KPI Review | 2026-10-22 | IT Infrastructure | Network Operations | Improve network monitoring reports | Network reports require manual compilation | Automate network monitoring reports | Improved network visibility | Medium | High | Network Administrator | Automate network monitoring reports | 2027-05-29 | Completed | 2027-05-28 | Effective | CI-EVD-042 | Aakanksha Abhay Mayekar | Closed | 2027-05-30 | Approved | Network monitoring reports automated
43 | CI-043 | Risk Assessment | 2026-10-24 | Risk Management | Risk Assessment | Standardize risk assessment evidence | Risk evidence is stored in multiple locations | Centralize risk assessment evidence | Better evidence availability | Low | Medium | Risk Manager | Centralize risk assessment evidence | 2027-06-05 | Completed | 2027-06-04 | Effective | CI-EVD-043 | Aakanksha Abhay Mayekar | Closed | 2027-06-06 | Approved | Risk assessment evidence centralized
44 | CI-044 | Management Review | 2026-10-26 | Management | Management Review | Improve management review KPI analysis | KPI analysis is performed manually | Implement automated KPI analysis | Faster KPI analysis | Low | Medium | ISMS Manager | Automate KPI analysis | 2027-06-12 | In Progress | - | Pending | CI-EVD-044 | Aakanksha Abhay Mayekar | Open | - | Pending | KPI analysis automated
45 | CI-045 | Internal Audit | 2026-10-28 | Compliance | Compliance Monitoring | Automate compliance reporting | Compliance reports require manual preparation | Automate compliance reporting | Reduced compliance reporting effort | Medium | High | Compliance Manager | Automate compliance reporting | 2027-06-19 | Completed | 2027-06-18 | Effective | CI-EVD-045 | Aakanksha Abhay Mayekar | Closed | 2027-06-20 | Approved | Compliance reporting improvement remains open
46 | CI-046 | Compliance Review | 2026-10-30 | Information Security | Information Security | Improve security control monitoring | Security controls are reviewed periodically | Implement continuous security control monitoring | Early identification of control weaknesses | High | Critical | Information Security Manager | Implement continuous security control monitoring | 2027-06-26 | Completed | 2027-06-25 | Effective | CI-EVD-046 | Aakanksha Abhay Mayekar | Closed | 2027-06-27 | Approved | Continuous security control monitoring implemented
47 | CI-047 | Security Incident | 2026-11-01 | Security Operations | Security Operations | Enhance security operations reporting | Security operations reports are manually consolidated | Centralize security operations reporting | Improved security operations visibility | Low | Medium | SOC Manager | Centralize security operations reporting | 2027-07-03 | In Progress | - | Pending | CI-EVD-047 | Aakanksha Abhay Mayekar | Open | - | Pending | Security operations reporting improved
48 | CI-048 | Employee Feedback | 2026-11-03 | Human Resources | Security Awareness | Improve employee security awareness feedback | Employee feedback is collected inconsistently | Implement structured employee security feedback process | Better employee feedback and engagement | Low | Medium | HR Manager | Implement employee security feedback process | 2027-07-10 | Completed | 2027-07-09 | Effective | CI-EVD-048 | Aakanksha Abhay Mayekar | Closed | 2027-07-11 | Approved | Employee feedback process improvement remains open
49 | CI-049 | KPI Review | 2026-11-05 | Information Security | ISMS Governance | Improve ISMS governance reporting | Governance reporting is manually prepared | Develop automated ISMS governance dashboard | Improved ISMS governance visibility | Low | Medium | CISO | Develop automated ISMS governance dashboard | 2027-07-17 | Completed | 2027-07-16 | Effective | CI-EVD-049 | Aakanksha Abhay Mayekar | Closed | 2027-07-18 | Approved | ISMS governance dashboard implemented
50 | CI-050 | Management Review | 2026-11-07 | Management | ISMS Governance | Improve ISMS governance reporting | Governance reporting is manually prepared | Develop automated ISMS governance dashboard | Improved ISMS governance visibility | Low | Medium | CISO | Develop automated ISMS governance dashboard | 2027-07-24 | Completed | - | Effective | CI-EVD-050 | Aakanksha Abhay Mayekar | Closed | - | Approved | ISMS governance dashboard implemented