## Sheet1
INTERNAL AUDIT REPORT REGISTER
Company Name : Mayekar Technologies Pvt. Ltd.
Document Number : MTPL-ISMS-022
Version : 1.0
Classification : Internal
Prepared By : Omkar Abhay Mayekar
Sr. No. | Report ID | Audit ID | Audit Date | Department | Lead Auditor | Major NC | Minor NC | Observations | OFI | Corrective Action Required | Responsible Person | Target Closure Date | Closure Status | Evidence Verified | Management Approval | Remarks
1 | IAR-001 | AUD-001 | 2026-08-05 | Information Security | Omkar Abhay Mayekar | 0 | 2 | Password policy requires improvement | Implement enterprise password manager | Update password policy | Information Security Manager | 2026-10-15 | Closed | Yes | Approved | Audit closed successfully
2 | IAR-002 | AUD-002 | 2026-08-08 | Human Resources | Omkar Abhay Mayekar | 0 | 1 | Backup verification process needs enhancement | Automate backup verification process | Improve backup verification process | Backup Administrator | 2026-10-20 | Closed | Yes | Approved | Evidence verified and accepted
3 | IAR-003 | AUD-003 | 2026-08-12 | IT Infrastructure | Omkar Abhay Mayekar | 1 | 3 | Patch deployment delay observed | Implement centralized patch management | Implement automated patch management | System Administrator | 2026-10-25 | Closed | Yes | Approved | Corrective actions implemented
4 | IAR-004 | AUD-004 | 2026-08-15 | Network Operations | Omkar Abhay Mayekar | 0 | 2 | Asset labels require updating | Deploy barcode/RFID asset tracking | Update asset labels | IT Asset Manager | 2026-10-30 | Closed | Yes | Approved | Department compliant
5 | IAR-005 | AUD-005 | 2026-08-19 | Asset Management | Omkar Abhay Mayekar | 0 | 1 | Visitor log incomplete | Introduce digital visitor management system | Digitize visitor log | Administration Manager | 2026-11-05 | Closed | Yes | Approved | Controls operating effectively
6 | IAR-006 | AUD-006 | 2026-08-22 | Administration | Omkar Abhay Mayekar | 0 | 2 | Access review documentation incomplete | Automate user access review workflow | Complete access review | HR Manager | 2026-11-10 | Closed | Yes | Approved | Follow-up completed
7 | IAR-007 | AUD-007 | 2026-08-26 | Access Management | Omkar Abhay Mayekar | 0 | 1 | Firewall documentation outdated | Perform quarterly firewall optimization | Update firewall documentation | Network Administrator | 2026-11-15 | In Progress | Pending | Pending | Corrective action under implementation
8 | IAR-008 | AUD-008 | 2026-08-29 | Risk Management | Omkar Abhay Mayekar | 1 | 2 | Network monitoring requires enhancement | Deploy SIEM with real-time dashboards | Improve network monitoring | Network Administrator | 2026-11-20 | Closed | Yes | Approved | Compliance achieved
9 | IAR-009 | AUD-009 | 2026-09-02 | Incident Management | Omkar Abhay Mayekar | 0 | 1 | Wi-Fi password rotation delayed | Upgrade all access points to WPA3 | Rotate Wi-Fi credentials | Network Administrator | 2026-11-25 | Closed | Yes | Approved | Security controls improved
10 | IAR-010 | AUD-010 | 2026-09-05 | Backup Management | Omkar Abhay Mayekar | 0 | 2 | UPS maintenance records incomplete | Implement predictive UPS monitoring | Update UPS maintenance schedule | IT Infrastructure Manager | 2026-11-30 | Closed | Yes | Approved | No further action required
11 | IAR-011 | AUD-011 | 2026-09-09 | Patch Management | Omkar Abhay Mayekar | 0 | 1 | Hardware inventory mismatch | Use automated asset lifecycle management | Reconcile hardware inventory | IT Asset Manager | 2026-12-05 | Closed | Yes | Approved | Records updated successfully
12 | IAR-012 | AUD-012 | 2026-09-12 | Change Management | Omkar Abhay Mayekar | 0 | 1 | USB control awareness required | Deploy enterprise Device Control solution | Conduct USB awareness training | IT Manager | 2026-12-10 | Closed | Yes | Approved | Audit objectives achieved
13 | IAR-013 | AUD-013 | 2026-09-16 | Vendor Management | Omkar Abhay Mayekar | 0 | 2 | Endpoint compliance below target | Enable real-time endpoint compliance dashboard | Improve endpoint compliance | Endpoint Security Administrator | 2026-12-15 | In Progress | Pending | Pending | Monitoring continues
14 | IAR-014 | AUD-014 | 2026-09-19 | Business Continuity | Omkar Abhay Mayekar | 1 | 2 | Risk review documentation incomplete | Implement automated risk dashboard | Complete risk review | Risk Manager | 2026-12-20 | Closed | Yes | Approved | Risk reduced to acceptable level
15 | IAR-015 | AUD-015 | 2026-09-23 | Disaster Recovery | Omkar Abhay Mayekar | 0 | 1 | Vendor assessment pending | Use vendor risk scoring system | Conduct vendor assessment | Procurement Manager | 2026-12-25 | Closed | Yes | Approved | Vendor compliance confirmed
16 | IAR-016 | AUD-016 | 2026-09-26 | Document Control | Omkar Abhay Mayekar | 0 | 2 | Document version history incomplete | Deploy electronic document approval workflow | Maintain document version history | Document Controller | 2026-12-30 | Closed | Yes | Approved | Documentation updated
17 | IAR-017 | AUD-017 | 2026-09-30 | Management Review | Omkar Abhay Mayekar | 0 | 1 | Management review minutes delayed | Automate management review reporting | Record management review minutes | Information Security Manager | 2027-01-05 | Closed | Yes | Approved | Management satisfied
18 | IAR-018 | AUD-018 | 2026-10-03 | Internal Audit | Omkar Abhay Mayekar | 0 | 1 | Internal audit checklist improvement required | Use digital internal audit management software | Update internal audit checklist | Lead Internal Auditor | 2027-01-10 | Closed | Yes | Approved | Audit officially closed
19 | IAR-019 | AUD-019 | 2026-10-07 | Training & Awareness | Omkar Abhay Mayekar | 1 | 2 | Training attendance records incomplete | Implement e-learning platform with quizzes | Maintain training records | HR Manager | 2027-01-15 | Closed | Yes | Approved | Training completed
20 | IAR-020 | AUD-020 | 2026-10-10 | Compliance | Omkar Abhay Mayekar | 0 | 1 | Compliance evidence incomplete | Deploy compliance monitoring dashboard | Collect compliance evidence | Compliance Manager | 2027-01-20 | Closed | Yes | Approved | Compliance maintained
21 | IAR-021 | AUD-021 | 2026-10-14 | Database Administration | Omkar Abhay Mayekar | 0 | 2 | Database review pending | Enable Database Activity Monitoring (DAM) | Review database security | Database Administrator | 2027-01-25 | In Progress | Pending | Pending | Pending verification
22 | IAR-022 | AUD-022 | 2026-10-17 | Cloud Operations | Omkar Abhay Mayekar | 0 | 1 | Cloud asset inventory incomplete | Implement Cloud Security Posture Management (CSPM) | Update cloud inventory | Cloud Administrator | 2027-01-30 | Closed | Yes | Approved | Cloud controls strengthened
23 | IAR-023 | AUD-023 | 2026-10-21 | Server Administration | Omkar Abhay Mayekar | 1 | 2 | Server hardening records missing | Automate server compliance checks | Complete server hardening | Server Administrator | 2027-02-05 | Closed | Yes | Approved | Server hardening verified
24 | IAR-024 | AUD-024 | 2026-10-24 | Endpoint Security | Omkar Abhay Mayekar | 0 | 1 | Endpoint monitoring dashboard incomplete | Deploy centralized endpoint management solution | Improve endpoint monitoring | Endpoint Security Administrator | 2027-02-10 | Closed | Yes | Approved | Endpoint protection effective
25 | IAR-025 | AUD-025 | 2026-10-28 | Application Security | Omkar Abhay Mayekar | 0 | 1 | Application review overdue | Integrate secure SDLC tools into CI/CD | Perform application review | Application Administrator | 2027-02-15 | Closed | Yes | Approved | Application controls improved
26 | IAR-026 | AUD-026 | 2026-10-31 | Web Security | Omkar Abhay Mayekar | 0 | 2 | Web security report delayed | Schedule automated web vulnerability scans | Complete web security assessment | Web Administrator | 2027-02-20 | Closed | Yes | Approved | Web security enhanced
27 | IAR-027 | AUD-027 | 2026-11-04 | Email Security | Omkar Abhay Mayekar | 0 | 1 | Email review documentation incomplete | Deploy advanced email threat protection | Review email security | Mail Administrator | 2027-02-25 | Closed | Yes | Approved | Email protection verified
28 | IAR-028 | AUD-028 | 2026-11-07 | Identity & Access Management | Omkar Abhay Mayekar | 1 | 2 | Privileged account review delayed | Implement Privileged Access Management (PAM) | Review privileged accounts | Active Directory Administrator | 2027-03-02 | In Progress | Pending | Pending | Access controls strengthened
29 | IAR-029 | AUD-029 | 2026-11-11 | Finance | Omkar Abhay Mayekar | 0 | 1 | Finance records require verification | Create finance security KPI dashboard | Verify finance records | Finance Manager | 2027-03-07 | Closed | Yes | Approved | Financial controls effective
30 | IAR-030 | AUD-030 | 2026-11-14 | Procurement | Omkar Abhay Mayekar | 0 | 2 | Procurement review pending | Automate supplier security assessments | Review procurement controls | Procurement Manager | 2027-03-12 | Closed | Yes | Approved | Procurement process compliant
31 | IAR-031 | AUD-031 | 2026-11-18 | Administration | Omkar Abhay Mayekar | 0 | 1 | Administrative SOP needs update | Digitize administration workflow | Update administrative SOP | Administration Manager | 2027-03-17 | Closed | Yes | Approved | Administrative process improved
32 | IAR-032 | AUD-032 | 2026-11-21 | IT Helpdesk | Omkar Abhay Mayekar | 0 | 1 | Helpdesk ticket categorization incomplete | Implement AI-based helpdesk ticket categorization | Improve helpdesk process | IT Helpdesk Manager | 2027-03-22 | Closed | Yes | Approved | Support process optimized
33 | IAR-033 | AUD-033 | 2026-11-25 | Information Classification | Omkar Abhay Mayekar | 1 | 2 | Information classification labels missing | Deploy automated data classification solution | Apply information classification labels | Information Security Manager | 2027-03-27 | Closed | Yes | Approved | Classification controls effective
34 | IAR-034 | AUD-034 | 2026-11-28 | Cryptography | Omkar Abhay Mayekar | 0 | 1 | Encryption review pending | Use centralized Key Management System (KMS) | Review encryption controls | Information Security Manager | 2027-04-01 | Closed | Yes | Approved | Encryption controls verified
35 | IAR-035 | AUD-035 | 2026-12-02 | Security Monitoring | Omkar Abhay Mayekar | 0 | 2 | Log review frequency inconsistent | Deploy centralized SIEM log analytics | Standardize log reviews | SOC Manager | 2027-04-06 | In Progress | Pending | Pending | Continuous monitoring active
36 | IAR-036 | AUD-036 | 2026-12-05 | Vulnerability Management | Omkar Abhay Mayekar | 0 | 1 | Vulnerability scan delayed | Implement continuous vulnerability scanning | Complete vulnerability scans | Vulnerability Manager | 2027-04-11 | Closed | Yes | Approved | Vulnerabilities remediated
37 | IAR-037 | AUD-037 | 2026-12-09 | Configuration Management | Omkar Abhay Mayekar | 0 | 1 | Configuration baseline outdated | Automate configuration compliance checks | Update configuration baseline | Configuration Manager | 2027-04-16 | Closed | Yes | Approved | Configuration baseline maintained
38 | IAR-038 | AUD-038 | 2026-12-12 | Capacity Management | Omkar Abhay Mayekar | 1 | 2 | Capacity report incomplete | Use capacity forecasting dashboards | Review capacity planning | Capacity Manager | 2027-04-21 | Closed | Yes | Approved | Capacity sufficient
39 | IAR-039 | AUD-039 | 2026-12-16 | Software Development | Omkar Abhay Mayekar | 0 | 1 | Secure coding evidence incomplete | Integrate DevSecOps practices | Maintain secure coding evidence | Development Manager | 2027-04-26 | Closed | Yes | Approved | Development controls effective
40 | IAR-040 | AUD-040 | 2026-12-19 | System Administration | Omkar Abhay Mayekar | 0 | 2 | System administration checklist incomplete | Automate server health monitoring | Complete admin checklist | System Administrator | 2027-05-01 | Closed | Yes | Approved | System administration compliant
41 | IAR-041 | AUD-041 | 2026-12-23 | Physical Security | Omkar Abhay Mayekar | 0 | 1 | Physical inspection report pending | Implement RFID-based physical asset tracking | Conduct physical inspection | Physical Security Manager | 2027-05-06 | Closed | Yes | Approved | Physical security maintained
42 | IAR-042 | AUD-042 | 2026-12-26 | Media Management | Omkar Abhay Mayekar | 0 | 1 | Media disposal records incomplete | Use certified media destruction service | Maintain media disposal records | Administration Manager | 2027-05-11 | In Progress | Pending | Pending | Awaiting final verification
43 | IAR-043 | AUD-043 | 2026-12-30 | Remote Access | Omkar Abhay Mayekar | 1 | 2 | VPN review pending | Adopt Zero Trust Network Access (ZTNA) | Review VPN configuration | Network Administrator | 2027-05-16 | Closed | Yes | Approved | Remote access secured
44 | IAR-044 | AUD-044 | 2027-01-02 | Third-Party Security | Omkar Abhay Mayekar | 0 | 1 | Third-party assessment delayed | Enable continuous third-party monitoring | Assess third-party security | Vendor Manager | 2027-05-21 | Closed | Yes | Approved | Third-party controls strengthened
45 | IAR-045 | AUD-045 | 2027-01-06 | Legal & Compliance | Omkar Abhay Mayekar | 0 | 2 | Legal register requires update | Implement legal compliance tracking software | Update legal compliance register | Compliance Manager | 2027-05-26 | Closed | Yes | Approved | Legal compliance achieved
46 | IAR-046 | AUD-046 | 2027-01-09 | Security Operations Centre (SOC) | Omkar Abhay Mayekar | 0 | 1 | SOC alert tuning required | Deploy SOAR for SOC automation | Tune SOC alerts | SOC Manager | 2027-05-31 | Closed | Yes | Approved | SOC performance improved
47 | IAR-047 | AUD-047 | 2027-01-13 | IT Support | Omkar Abhay Mayekar | 0 | 1 | IT support metrics incomplete | Integrate ITSM with security monitoring | Improve IT support reporting | IT Support Manager | 2027-06-05 | Closed | Yes | Approved | Support metrics achieved
48 | IAR-048 | AUD-048 | 2027-01-16 | Network Operations Centre (NOC) | Omkar Abhay Mayekar | 1 | 2 | NOC report pending | Deploy Network Performance Monitoring (NPM) | Review NOC operations | NOC Manager | 2027-06-10 | Closed | Yes | Approved | Network operations stable
49 | IAR-049 | AUD-049 | 2027-01-20 | ISMS Performance | Omkar Abhay Mayekar | 0 | 1 | KPI review delayed | Create automated ISMS KPI dashboard | Review ISMS KPIs | Information Security Manager | 2027-06-15 | In Progress | Pending | Pending | ISMS objectives achieved
50 | IAR-050 | AUD-050 | 2027-01-23 | Continual Improvement | Omkar Abhay Mayekar | 0 | 1 | Continual improvement actions pending | Maintain Continual Improvement Dashboard | Implement continual improvement actions | Chief Information Security Officer (CISO) | 2027-06-20 | Closed | Yes | Approved | Audit formally closed