## Sheet1
MANAGEMENT REVIEW MEETING MINUTES & ACTION TRACKER
Company Name : Mayekar Technologies Pvt. Ltd.
Document Number : MTPL-ISMS-024
Version : 1.0
Classification : Internal
Prepared By : Omkar Abhay Mayekar
Sr. No. | Minutes ID | MRM ID | Meeting Date | Agenda / Review Input | Discussion Summary | Decision / Conclusion | Action Item | Action Owner | Priority | Target Date | Status | Completion Date | Evidence / Attachment | Management Approval | Remarks
1 | MIN-001 | MRM-001 | 2026-08-10 | ISMS objectives and KPI performance | ISMS objectives were reviewed and KPI performance was assessed | Continue monitoring ISMS objectives and KPIs | Monitor ISMS objectives and KPI performance | Information Security Manager | High | 2026-08-15 | Completed | 2026-08-14 | MRM-MIN-001; KPI-REPORT-001 | Approved | KPI review completed successfully
2 | MIN-002 | MRM-002 | 2026-08-17 | Risk assessment and risk treatment status | Risk treatment progress and outstanding risks were reviewed | Complete outstanding risk treatment actions | Complete outstanding risk treatment actions | Risk Manager | High | 2026-08-22 | Completed | 2026-08-21 | MRM-MIN-002; RISK-REG-001 | Approved | Risk treatment action approved
3 | MIN-003 | MRM-003 | 2026-08-24 | Internal audit results and findings | Internal audit findings and closure status were discussed | Close verified internal audit findings | Close internal audit findings | Lead Internal Auditor | High | 2026-08-29 | Completed | 2026-08-28 | MRM-MIN-003; IAR-001 | Approved | Internal audit finding reviewed
4 | MIN-004 | MRM-004 | 2026-08-31 | Information security incident trends | Security incident trends and response effectiveness were evaluated | Maintain current incident response controls | Review information security incident trends | Incident Manager | Medium | 2026-09-05 | In Progress | - | MRM-MIN-004; INCIDENT-001 | Pending | Incident trends reviewed
5 | MIN-005 | MRM-005 | 2026-09-07 | Corrective action status | Open corrective actions were reviewed with responsible owners | Accelerate overdue corrective actions | Complete overdue corrective actions | Compliance Manager | High | 2026-09-12 | Completed | 2026-09-11 | MRM-MIN-005; CAR-001 | Approved | Corrective action progress accepted
6 | MIN-006 | MRM-006 | 2026-09-14 | Preventive action status | Preventive actions were reviewed for effectiveness | Continue preventive controls and monitor effectiveness | Review preventive action effectiveness | Information Security Manager | Medium | 2026-09-19 | Completed | 2026-09-18 | MRM-MIN-006; PAR-001 | Approved | Preventive action effectiveness confirmed
7 | MIN-007 | MRM-007 | 2026-09-21 | Asset management performance | Asset inventory accuracy and lifecycle management were discussed | Complete asset inventory reconciliation | Reconcile asset inventory | IT Asset Manager | High | 2026-09-26 | In Progress | - | MRM-MIN-007; ASSET-REG-001 | Pending | Asset reconciliation action initiated
8 | MIN-008 | MRM-008 | 2026-09-28 | Access control effectiveness | User access review results were evaluated | Perform scheduled access review | Complete user access review | IAM Administrator | High | 2026-10-03 | Completed | 2026-10-02 | MRM-MIN-008; ACCESS-REV-001 | Approved | Access review completed
9 | MIN-009 | MRM-009 | 2026-10-05 | Security monitoring performance | Security monitoring coverage and alert handling were reviewed | Improve security monitoring coverage | Improve security monitoring coverage | SOC Manager | High | 2026-10-10 | Completed | 2026-10-09 | MRM-MIN-009; SOC-REPORT-001 | Approved | Security monitoring improvement approved
10 | MIN-010 | MRM-010 | 2026-10-12 | Backup and recovery performance | Backup success and restoration testing results were discussed | Continue backup verification and restoration testing | Perform backup restoration test | Backup Administrator | High | 2026-10-17 | Completed | 2026-10-16 | MRM-MIN-010; BACKUP-REPORT-001 | Approved | Backup testing completed
11 | MIN-011 | MRM-011 | 2026-10-19 | Patch management status | Patch compliance and outstanding vulnerabilities were reviewed | Accelerate patch remediation | Complete pending security patches | System Administrator | High | 2026-10-24 | In Progress | - | MRM-MIN-011; PATCH-REPORT-001 | Pending | Patch remediation monitored
12 | MIN-012 | MRM-012 | 2026-10-26 | Change management performance | Recent changes were assessed for security impact | Maintain controlled change management | Review recent changes for security impact | Change Manager | Medium | 2026-10-31 | Completed | 2026-10-30 | MRM-MIN-012; CHANGE-REG-001 | Approved | Change management review completed
13 | MIN-013 | MRM-013 | 2026-11-02 | Supplier security performance | Supplier security assessments and outstanding actions were reviewed | Complete pending supplier assessments | Complete supplier security assessments | Vendor Manager | High | 2026-11-07 | Completed | 2026-11-06 | MRM-MIN-013; VENDOR-ASS-001 | Approved | Supplier security action approved
14 | MIN-014 | MRM-014 | 2026-11-09 | Business continuity status | Business continuity arrangements were evaluated | Maintain business continuity arrangements | Update business continuity arrangements | Business Continuity Manager | Medium | 2026-11-14 | In Progress | - | MRM-MIN-014; BCP-001 | Pending | Business continuity arrangements reviewed
15 | MIN-015 | MRM-015 | 2026-11-16 | Disaster recovery readiness | Disaster recovery readiness and test results were discussed | Conduct scheduled disaster recovery testing | Conduct disaster recovery test | Disaster Recovery Manager | High | 2026-11-21 | Completed | 2026-11-20 | MRM-MIN-015; DR-TEST-001 | Approved | DR testing action approved
16 | MIN-016 | MRM-016 | 2026-11-23 | ISMS documentation status | ISMS documents requiring review or update were identified | Update identified ISMS documents | Update controlled ISMS documents | Document Controller | Medium | 2026-11-28 | Completed | 2026-11-27 | MRM-MIN-016; DOC-REG-001 | Approved | ISMS documentation update initiated
17 | MIN-017 | MRM-017 | 2026-11-30 | Management review actions | Previous management review actions were reviewed | Track all management review actions to closure | Close previous management review actions | Information Security Manager | High | 2026-12-05 | Completed | 2026-12-04 | MRM-MIN-017; MRM-ACTION-001 | Approved | Management action follow-up completed
18 | MIN-018 | MRM-018 | 2026-12-07 | Security awareness performance | Security awareness completion and effectiveness were discussed | Continue security awareness activities | Complete security awareness activities | HR Manager | Medium | 2026-12-12 | Completed | 2026-12-11 | MRM-MIN-018; TRAINING-REG-001 | Approved | Security awareness progress reviewed
19 | MIN-019 | MRM-019 | 2026-12-14 | Compliance obligations status | Applicable compliance obligations were reviewed | Maintain compliance monitoring | Update compliance evidence | Compliance Manager | High | 2026-12-19 | In Progress | - | MRM-MIN-019; COMPLIANCE-REG-001 | Pending | Compliance evidence verified
20 | MIN-020 | MRM-020 | 2026-12-21 | Database security performance | Database security controls and access logs were evaluated | Strengthen database security monitoring | Strengthen database security monitoring | Database Administrator | High | 2026-12-26 | Completed | 2026-12-25 | MRM-MIN-020; DB-AUDIT-001 | Approved | Database security review completed
21 | MIN-021 | MRM-021 | 2026-12-28 | Cloud security posture | Cloud security controls and configuration status were reviewed | Improve cloud security posture | Improve cloud security configuration | Cloud Administrator | High | 2027-01-02 | Completed | 2027-01-01 | MRM-MIN-021; CLOUD-AUDIT-001 | Approved | Cloud security improvement approved
22 | MIN-022 | MRM-022 | 2027-01-04 | Server security status | Server hardening and security baseline compliance were discussed | Maintain server security baselines | Complete server hardening activities | Server Administrator | High | 2027-01-09 | In Progress | - | MRM-MIN-022; SERVER-AUDIT-001 | Pending | Server hardening action monitored
23 | MIN-023 | MRM-023 | 2027-01-11 | Endpoint security status | Endpoint security coverage and compliance were reviewed | Improve endpoint compliance | Improve endpoint compliance | Endpoint Security Administrator | High | 2027-01-16 | Completed | 2027-01-15 | MRM-MIN-023; EDR-REPORT-001 | Approved | Endpoint security improvement required
24 | MIN-024 | MRM-024 | 2027-01-18 | Application security performance | Application security testing and remediation status were discussed | Complete application security remediation | Complete application security remediation | Application Security Manager | High | 2027-01-23 | Completed | 2027-01-22 | MRM-MIN-024; APP-SEC-001 | Approved | Application security action approved
25 | MIN-025 | MRM-025 | 2027-01-25 | Web security status | Web security monitoring and vulnerability status were reviewed | Continue web security monitoring | Conduct web security assessment | Web Administrator | Medium | 2027-01-30 | Completed | 2027-01-29 | MRM-MIN-025; WEB-AUDIT-001 | Approved | Web security assessment completed
26 | MIN-026 | MRM-026 | 2027-02-01 | Email security performance | Email security controls and threat trends were discussed | Strengthen email security controls | Strengthen email security controls | Mail Administrator | High | 2027-02-06 | In Progress | - | MRM-MIN-026; EMAIL-REPORT-001 | Pending | Email security controls reviewed
27 | MIN-027 | MRM-027 | 2027-02-08 | Privileged access management | Privileged access reviews and exceptions were evaluated | Complete privileged access review | Complete privileged access review | IAM Administrator | High | 2027-02-13 | Completed | 2027-02-12 | MRM-MIN-027; PAM-REVIEW-001 | Approved | Privileged access review initiated
28 | MIN-028 | MRM-028 | 2027-02-15 | Financial information security | Financial information security controls were reviewed | Maintain financial security controls | Review financial information security controls | Finance Manager | Medium | 2027-02-20 | Completed | 2027-02-19 | MRM-MIN-028; FIN-AUDIT-001 | Approved | Financial security controls reviewed
29 | MIN-029 | MRM-029 | 2027-02-22 | Procurement security controls | Procurement security requirements were assessed | Strengthen procurement security requirements | Complete procurement security assessment | Procurement Manager | Medium | 2027-02-27 | In Progress | - | MRM-MIN-029; PROC-AUDIT-001 | Pending | Procurement security action approved
30 | MIN-030 | MRM-030 | 2027-03-01 | Administrative security controls | Administrative security procedures were reviewed | Update administrative procedures | Update administrative procedures | Administration Manager | Medium | 2027-03-06 | Completed | 2027-03-05 | MRM-MIN-030; ADMIN-REVIEW-001 | Approved | Administrative controls reviewed
31 | MIN-031 | MRM-031 | 2027-03-08 | IT support performance | IT support performance and security-related tickets were discussed | Improve IT support security metrics | Improve IT support security reporting | IT Helpdesk Manager | Medium | 2027-03-13 | Completed | 2027-03-12 | MRM-MIN-031; ITSM-REPORT-001 | Approved | IT support performance reviewed
32 | MIN-032 | MRM-032 | 2027-03-15 | Information classification status | Information classification implementation was reviewed | Complete information classification implementation | Complete information classification implementation | Information Security Manager | High | 2027-03-20 | Completed | 2027-03-19 | MRM-MIN-032; DATA-CLASS-001 | Approved | Data classification action approved
33 | MIN-033 | MRM-033 | 2027-03-22 | Cryptographic controls | Cryptographic controls and encryption compliance were evaluated | Maintain encryption controls | Review encryption compliance | Security Administrator | High | 2027-03-27 | In Progress | - | MRM-MIN-033; CRYPTO-AUDIT-001 | Pending | Encryption controls verified
34 | MIN-034 | MRM-034 | 2027-03-29 | Logging and monitoring effectiveness | Logging coverage and monitoring effectiveness were reviewed | Improve centralized logging coverage | Improve centralized logging | SOC Manager | High | 2027-04-03 | Completed | 2027-04-02 | MRM-MIN-034; SIEM-REPORT-001 | Approved | Logging improvement approved
35 | MIN-035 | MRM-035 | 2027-04-05 | Vulnerability management status | Vulnerability assessment results and remediation progress were discussed | Accelerate vulnerability remediation | Complete vulnerability remediation | Vulnerability Manager | High | 2027-04-10 | Completed | 2027-04-09 | MRM-MIN-035; VAPT-REPORT-001 | Approved | Vulnerability remediation monitored
36 | MIN-036 | MRM-036 | 2027-04-12 | Configuration management status | Configuration baseline compliance was reviewed | Enforce configuration baselines | Enforce configuration baselines | Configuration Manager | High | 2027-04-17 | In Progress | - | MRM-MIN-036; CONFIG-AUDIT-001 | Pending | Configuration baseline reviewed
37 | MIN-037 | MRM-037 | 2027-04-19 | Capacity management status | Infrastructure capacity and resource requirements were discussed | Review capacity requirements periodically | Review infrastructure capacity | Capacity Manager | Medium | 2027-04-24 | Completed | 2027-04-23 | MRM-MIN-037; CAPACITY-REPORT-001 | Approved | Capacity requirements assessed
38 | MIN-038 | MRM-038 | 2027-04-26 | Secure development practices | Secure development practices and security testing were reviewed | Strengthen secure development controls | Strengthen secure development controls | Development Manager | High | 2027-05-01 | Completed | 2027-04-30 | MRM-MIN-038; SSDLC-REVIEW-001 | Approved | Secure development action approved
39 | MIN-039 | MRM-039 | 2027-05-03 | System administration controls | System administration controls and privileged activities were discussed | Maintain system administration procedures | Update system administration checklist | System Administrator | Medium | 2027-05-08 | In Progress | - | MRM-MIN-039; SYSADMIN-CHK-001 | Pending | System administration controls reviewed
40 | MIN-040 | MRM-040 | 2027-05-10 | Physical security controls | Physical security controls and access records were reviewed | Continue physical security monitoring | Complete physical security inspection | Physical Security Manager | Medium | 2027-05-15 | Completed | 2027-05-14 | MRM-MIN-040; PHYSICAL-AUDIT-001 | Approved | Physical security inspection planned
41 | MIN-041 | MRM-041 | 2027-05-17 | Media handling controls | Media handling and disposal practices were evaluated | Improve media disposal tracking | Improve media disposal tracking | Media Management Officer | High | 2027-05-22 | Completed | 2027-05-21 | MRM-MIN-041; MEDIA-DISPOSAL-001 | Approved | Media disposal controls reviewed
42 | MIN-042 | MRM-042 | 2027-05-24 | Remote access security | Remote access security controls were reviewed | Strengthen remote access controls | Review remote access security | Network Administrator | High | 2027-05-29 | In Progress | - | MRM-MIN-042; VPN-AUDIT-001 | Pending | Remote access controls strengthened
43 | MIN-043 | MRM-043 | 2027-05-31 | Third-party security risks | Third-party security risks and supplier actions were discussed | Increase third-party security monitoring | Complete third-party security assessment | Vendor Manager | High | 2027-06-05 | Completed | 2027-06-04 | MRM-MIN-043; SUPPLIER-REVIEW-001 | Approved | Third-party security action initiated
44 | MIN-044 | MRM-044 | 2027-06-07 | Legal and regulatory compliance | Legal and regulatory compliance status was reviewed | Maintain legal and regulatory compliance | Update legal compliance register | Compliance Manager | High | 2027-06-12 | Completed | 2027-06-11 | MRM-MIN-044; LEGAL-REG-001 | Approved | Legal compliance update approved
45 | MIN-045 | MRM-045 | 2027-06-14 | SOC performance | SOC performance and security alert trends were evaluated | Improve SOC monitoring and alert tuning | Tune SOC security alerts | SOC Manager | High | 2027-06-19 | Completed | 2027-06-18 | MRM-MIN-045; SOC-REPORT-002 | Approved | SOC improvement action approved
46 | MIN-046 | MRM-046 | 2027-06-21 | IT support metrics | IT support metrics and service performance were reviewed | Improve IT support reporting | Improve IT support metrics | IT Support Manager | Medium | 2027-06-26 | In Progress | 2027-06-25 | MRM-MIN-046; ITSUPPORT-REPORT-001 | Pending | IT support metrics reviewed
47 | MIN-047 | MRM-047 | 2027-06-28 | NOC performance | NOC monitoring and network availability were discussed | Strengthen NOC monitoring | Strengthen NOC monitoring | NOC Manager | High | 2027-07-03 | Completed | - | MRM-MIN-047; NOC-REPORT-001 | Approved | NOC monitoring improvement approved
48 | MIN-048 | MRM-048 | 2027-07-05 | ISMS performance indicators | ISMS objectives and performance indicators were reviewed | Continue KPI monitoring | Review ISMS performance indicators | Information Security Manager | Medium | 2027-07-10 | Completed | 2027-07-09 | MRM-MIN-048; KPI-REPORT-002 | Approved | ISMS KPI performance reviewed
49 | MIN-049 | MRM-049 | 2027-07-12 | Continual improvement opportunities | Improvement opportunities and proposed initiatives were discussed | Implement approved improvement opportunities | Implement approved improvement initiatives | Chief Information Security Officer (CISO) | High | 2027-07-17 | In Progress | 2027-07-16 | MRM-MIN-049; IMPROVEMENT-REG-001 | Pending | Continual improvement action approved
50 | MIN-050 | MRM-050 | 2027-07-19 | Overall ISMS suitability, adequacy and effectiveness | Overall suitability, adequacy and effectiveness of the ISMS were evaluated | Maintain overall ISMS effectiveness | Review overall ISMS effectiveness | Chief Information Security Officer (CISO) | High | 2027-07-24 | Completed | - | MRM-MIN-050; ISMS-REVIEW-001 | Approved | Overall ISMS effectiveness confirmed