## Sheet1
MANAGEMENT REVIEW MEETING REGISTER
Company Name : Mayekar Technologies Pvt. Ltd.
Document Number : MTPL-ISMS-023
Version : 1.0
Classification : Internal
Prepared By : Omkar Abhay Mayekar
Sr. No. | MRM ID | Meeting Date | Meeting Type | Meeting Chairperson | Participants | ISMS Performance Reviewed | Internal Audit Status | Risk Status | KPI / Objective Status | Incident Status | Management Decision | Action Required | Action Owner | Target Date | Action Status | Evidence / Minutes Reference | Remarks
1 | MRM-001 | 2026-08-10 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Omkar Abhay Mayekar | ISMS objectives and KPI performance | Completed | Under Control | Achieved | No Major Incidents | Continue existing ISMS controls | Continue monitoring ISMS performance | Information Security Manager | 2026-08-15 | Completed | MRM-MIN-001 | ISMS performance reviewed successfully
2 | MRM-002 | 2026-08-17 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Omkar Abhay Mayekar | Risk treatment progress | Completed | Risk Treatment In Progress | In Progress | No Major Incidents | Accelerate risk treatment activities | Complete outstanding risk treatments | Risk Manager | 2026-08-22 | Completed | MRM-MIN-002 | Risk treatment progress reviewed
3 | MRM-003 | 2026-08-24 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; IT Infrastructure Manager | Internal audit performance | Completed | Under Control | Achieved | Minor Incidents Reviewed | Maintain current security controls | Maintain existing controls | Information Security Manager | 2026-08-29 | Completed | MRM-MIN-003 | Security controls remain effective
4 | MRM-004 | 2026-08-31 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Network Administrator | Information security incidents | Completed | Under Control | Achieved | No Major Incidents | Approve additional monitoring | Implement additional security monitoring | Network Administrator | 2026-09-05 | In Progress | MRM-MIN-004 | Network monitoring improvement initiated
5 | MRM-005 | 2026-09-07 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; HR Manager | Asset management performance | Completed | Risk Treatment In Progress | In Progress | No Major Incidents | Strengthen asset management process | Update asset inventory | IT Asset Manager | 2026-09-12 | Completed | MRM-MIN-005 | Asset inventory review completed
6 | MRM-006 | 2026-09-14 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Information Security Manager | Access control effectiveness | Completed | Under Control | Achieved | Minor Incidents Reviewed | Maintain physical security controls | Complete physical security review | Physical Security Manager | 2026-09-19 | Completed | MRM-MIN-006 | Physical security controls maintained
7 | MRM-007 | 2026-09-21 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Risk Manager | Network security performance | In Progress | Risk Treatment Required | In Progress | Incident Investigation Ongoing | Prioritize access control improvements | Complete access control review | IAM Administrator | 2026-09-26 | In Progress | MRM-MIN-007 | Access review action initiated
8 | MRM-008 | 2026-09-28 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Security Operations Manager | Security monitoring performance | Completed | Under Control | Achieved | No Major Incidents | Approve risk treatment plan | Update risk treatment plan | Risk Manager | 2026-10-03 | Completed | MRM-MIN-008 | Risk treatment plan updated
9 | MRM-009 | 2026-10-05 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Backup Administrator | Backup and recovery performance | Completed | Under Control | Achieved | Backup Incident Reviewed | Maintain current incident response process | Review incident response effectiveness | Incident Manager | 2026-10-10 | Completed | MRM-MIN-009 | Incident response effectiveness confirmed
10 | MRM-010 | 2026-10-12 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; System Administrator | Patch management performance | Completed | Under Control | Achieved | No Major Incidents | Approve backup improvements | Improve backup verification | Backup Administrator | 2026-10-17 | Completed | MRM-MIN-010 | Backup controls reviewed
11 | MRM-011 | 2026-10-19 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; IT Manager | Change management effectiveness | Completed | Risk Treatment In Progress | In Progress | Patch-Related Incident Reviewed | Accelerate patch management | Complete pending patches | System Administrator | 2026-10-24 | In Progress | MRM-MIN-011 | Patch management improvement ongoing
12 | MRM-012 | 2026-10-26 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Change Manager | Supplier security performance | Completed | Under Control | Achieved | No Major Incidents | Maintain change management controls | Review change management records | Change Manager | 2026-10-31 | Completed | MRM-MIN-012 | Change management controls effective
13 | MRM-013 | 2026-11-02 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Procurement Manager | Business continuity readiness | Completed | Under Control | Achieved | Vendor Incident Reviewed | Strengthen supplier security | Complete supplier security assessments | Vendor Manager | 2026-11-07 | Completed | MRM-MIN-013 | Supplier security review completed
14 | MRM-014 | 2026-11-09 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Business Continuity Manager | Disaster recovery readiness | Completed | Risk Treatment In Progress | In Progress | No Major Incidents | Approve continuity improvements | Update business continuity plan | Business Continuity Manager | 2026-11-14 | In Progress | MRM-MIN-014 | Business continuity actions progressing
15 | MRM-015 | 2026-11-16 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Disaster Recovery Manager | Document control performance | Completed | Under Control | Achieved | DR Exercise Reviewed | Conduct additional DR testing | Conduct DR testing | Disaster Recovery Manager | 2026-11-21 | Completed | MRM-MIN-015 | DR preparedness reviewed
16 | MRM-016 | 2026-11-23 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Document Controller | Management review action status | Completed | Under Control | Achieved | No Major Incidents | Improve document control | Update controlled documents | Document Controller | 2026-11-28 | Completed | MRM-MIN-016 | Document control requirements reinforced
17 | MRM-017 | 2026-11-30 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Information Security Manager | Internal audit findings | Completed | Risk Treatment In Progress | In Progress | Audit-Related Findings Reviewed | Address internal audit findings | Close internal audit findings | Lead Internal Auditor | 2026-12-05 | Completed | MRM-MIN-017 | Internal audit findings reviewed
18 | MRM-018 | 2026-12-07 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Lead Internal Auditor | Security awareness performance | Completed | Under Control | Achieved | No Major Incidents | Continue security awareness program | Complete awareness training | HR Manager | 2026-12-12 | Completed | MRM-MIN-018 | Security awareness progress satisfactory
19 | MRM-019 | 2026-12-14 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; HR Manager | Compliance status | Completed | Under Control | Achieved | Security Awareness Issues Reviewed | Strengthen compliance monitoring | Update compliance evidence | Compliance Manager | 2026-12-19 | In Progress | MRM-MIN-019 | Compliance status reviewed
20 | MRM-020 | 2026-12-21 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Compliance Manager | Database security performance | Completed | Under Control | Achieved | No Major Incidents | Maintain database security controls | Complete database security review | Database Administrator | 2026-12-26 | Completed | MRM-MIN-020 | Database security controls effective
21 | MRM-021 | 2026-12-28 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Database Administrator | Cloud security performance | In Progress | Risk Treatment Required | In Progress | Database Incident Reviewed | Prioritize cloud security improvements | Review cloud security controls | Cloud Administrator | 2027-01-02 | Completed | MRM-MIN-021 | Cloud security improvement ongoing
22 | MRM-022 | 2027-01-04 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Cloud Administrator | Server security performance | Completed | Under Control | Achieved | No Major Incidents | Maintain server security standards | Complete server hardening | Server Administrator | 2027-01-09 | In Progress | MRM-MIN-022 | Server security controls maintained
23 | MRM-023 | 2027-01-11 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Server Administrator | Endpoint security performance | Completed | Under Control | Achieved | Cloud Security Event Reviewed | Improve endpoint compliance | Improve endpoint compliance | Endpoint Security Administrator | 2027-01-16 | Completed | MRM-MIN-023 | Endpoint compliance improvement required
24 | MRM-024 | 2027-01-18 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Endpoint Security Administrator | Application security performance | Completed | Risk Treatment In Progress | In Progress | No Major Incidents | Approve application security enhancements | Complete application security testing | Application Security Manager | 2027-01-23 | Completed | MRM-MIN-024 | Application security actions progressing
25 | MRM-025 | 2027-01-25 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Application Administrator | Web security performance | Completed | Under Control | Achieved | Endpoint Incident Reviewed | Continue web security monitoring | Perform web security assessment | Web Administrator | 2027-01-30 | Completed | MRM-MIN-025 | Web security controls effective
26 | MRM-026 | 2027-02-01 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Web Administrator | Email security performance | Completed | Under Control | Achieved | No Major Incidents | Strengthen email security | Review email security controls | Mail Administrator | 2027-02-06 | In Progress | MRM-MIN-026 | Email security reviewed
27 | MRM-027 | 2027-02-08 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Mail Administrator | Identity and access management | Completed | Risk Treatment In Progress | In Progress | Web Security Event Reviewed | Review privileged access controls | Complete privileged access review | IAM Administrator | 2027-02-13 | Completed | MRM-MIN-027 | Privileged access controls reviewed
28 | MRM-028 | 2027-02-15 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Active Directory Administrator | Financial information security | In Progress | Under Control | Achieved | No Major Incidents | Maintain financial security controls | Review finance security controls | Finance Manager | 2027-02-20 | Completed | MRM-MIN-028 | Financial security controls satisfactory
29 | MRM-029 | 2027-02-22 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Finance Manager | Procurement security | Completed | Under Control | Achieved | Access Violation Reviewed | Strengthen procurement controls | Complete procurement assessment | Procurement Manager | 2027-02-27 | In Progress | MRM-MIN-029 | Procurement controls reviewed
30 | MRM-030 | 2027-03-01 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Procurement Manager | Administrative security | Completed | Under Control | Achieved | No Major Incidents | Update administrative procedures | Update administrative SOPs | Administration Manager | 2027-03-06 | Completed | MRM-MIN-030 | Administrative procedures updated
31 | MRM-031 | 2027-03-08 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Administration Manager | IT support performance | Completed | Risk Treatment Required | In Progress | Phishing Incidents Reviewed | Improve IT support monitoring | Improve helpdesk reporting | IT Helpdesk Manager | 2027-03-13 | Completed | MRM-MIN-031 | IT support performance reviewed
32 | MRM-032 | 2027-03-15 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; IT Helpdesk Manager | Information classification compliance | Completed | Under Control | Achieved | No Major Incidents | Implement data classification improvements | Complete data classification exercise | Information Security Manager | 2027-03-20 | Completed | MRM-MIN-032 | Data classification improvements initiated
33 | MRM-033 | 2027-03-22 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Information Security Manager | Cryptographic control effectiveness | Completed | Under Control | Achieved | Data Classification Issue Reviewed | Strengthen cryptographic controls | Review encryption controls | Information Security Manager | 2027-03-27 | In Progress | MRM-MIN-033 | Cryptographic controls reviewed
34 | MRM-034 | 2027-03-29 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Security Architect | Security logging and monitoring | Completed | Risk Treatment In Progress | In Progress | No Major Incidents | Improve centralized logging | Improve log monitoring | SOC Manager | 2027-04-03 | Completed | MRM-MIN-034 | Logging improvements approved
35 | MRM-035 | 2027-04-05 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; SOC Manager | Vulnerability management | In Progress | Under Control | Achieved | Logging Alert Reviewed | Accelerate vulnerability remediation | Complete vulnerability remediation | Vulnerability Manager | 2027-04-10 | Completed | MRM-MIN-035 | Vulnerability remediation monitored
36 | MRM-036 | 2027-04-12 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Vulnerability Manager | Configuration management | Completed | Under Control | Achieved | Vulnerability Incident Reviewed | Maintain configuration baselines | Update configuration baseline | Configuration Manager | 2027-04-17 | In Progress | MRM-MIN-036 | Configuration controls reviewed
37 | MRM-037 | 2027-04-19 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Configuration Manager | Capacity management | Completed | Under Control | Achieved | No Major Incidents | Review capacity requirements | Review capacity plan | Capacity Manager | 2027-04-24 | Completed | MRM-MIN-037 | Capacity requirements assessed
38 | MRM-038 | 2027-04-26 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Capacity Manager | Secure software development | Completed | Risk Treatment In Progress | In Progress | Configuration Issue Reviewed | Strengthen secure development practices | Complete secure development review | Development Manager | 2027-05-01 | Completed | MRM-MIN-038 | Secure development controls reviewed
39 | MRM-039 | 2027-05-03 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Development Manager | System administration | Completed | Under Control | Achieved | No Major Incidents | Maintain system administration controls | Update system administration checklist | System Administrator | 2027-05-08 | In Progress | MRM-MIN-039 | System administration controls effective
40 | MRM-040 | 2027-05-10 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; System Administrator | Physical security | Completed | Under Control | Achieved | Application Security Incident Reviewed | Improve physical asset protection | Complete physical security inspection | Physical Security Manager | 2027-05-15 | Completed | MRM-MIN-040 | Physical security inspection scheduled
41 | MRM-041 | 2027-05-17 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Physical Security Manager | Media handling | Completed | Risk Treatment In Progress | In Progress | No Major Incidents | Strengthen media handling | Review media disposal controls | Media Management Officer | 2027-05-22 | Completed | MRM-MIN-041 | Media handling controls reviewed
42 | MRM-042 | 2027-05-24 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Media Management Officer | Remote access security | In Progress | Under Control | Achieved | Physical Security Incident Reviewed | Enhance remote access security | Complete VPN security review | Network Administrator | 2027-05-29 | In Progress | MRM-MIN-042 | Remote access security strengthened
43 | MRM-043 | 2027-05-31 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Network Administrator | Third-party security | Completed | Under Control | Achieved | No Major Incidents | Increase third-party monitoring | Complete third-party security review | Vendor Manager | 2027-06-05 | Completed | MRM-MIN-043 | Third-party security monitoring continued
44 | MRM-044 | 2027-06-07 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; Vendor Manager | Legal and regulatory compliance | Completed | Risk Treatment Required | In Progress | Remote Access Incident Reviewed | Update legal compliance tracking | Update legal register | Compliance Manager | 2027-06-12 | Completed | MRM-MIN-044 | Legal compliance status reviewed
45 | MRM-045 | 2027-06-14 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Compliance Manager | SOC performance | Completed | Under Control | Achieved | Third-Party Incident Reviewed | Improve SOC monitoring capability | Tune SOC alerts | SOC Manager | 2027-06-19 | Completed | MRM-MIN-045 | SOC performance reviewed
46 | MRM-046 | 2027-06-21 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; SOC Manager | IT support metrics | Completed | Under Control | Achieved | No Major Incidents | Improve IT support metrics | Improve IT support metrics | IT Support Manager | 2027-06-26 | In Progress | MRM-MIN-046 | IT support metrics reviewed
47 | MRM-047 | 2027-06-28 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; IT Support Manager | Network operations performance | Completed | Risk Treatment In Progress | In Progress | SOC Alerts Reviewed | Strengthen NOC monitoring | Review NOC monitoring | NOC Manager | 2027-07-03 | Completed | MRM-MIN-047 | NOC performance reviewed
48 | MRM-048 | 2027-07-05 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Omkar Abhay Mayekar; NOC Manager | ISMS KPI performance | Completed | Under Control | Achieved | No Major Incidents | Continue KPI monitoring | Review ISMS objectives and KPIs | Information Security Manager | 2027-07-10 | Completed | MRM-MIN-048 | ISMS objectives reviewed
49 | MRM-049 | 2027-07-12 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Information Security Manager | Continual improvement progress | In Progress | Under Control | In Progress | NOC Events Reviewed | Approve continual improvement actions | Implement improvement actions | Chief Information Security Officer (CISO) | 2027-07-17 | In Progress | MRM-MIN-049 | Continual improvement actions approved
50 | MRM-050 | 2027-07-19 | Monthly ISMS Review | Aakanksha Abhay Mayekar | Aakanksha Abhay Mayekar; Alankar Abhay Mayekar; Information Security Manager | Overall ISMS effectiveness | Completed | Under Control | Achieved | No Major Incidents | Maintain overall ISMS effectiveness | Complete management review follow-up | Chief Information Security Officer (CISO) | 2027-07-24 | Completed | MRM-MIN-050 | Management review follow-up completed